## Register
Risk ID | Risk Name | Asset | Threat | Vulnerability | Likelihood (1-5) | Impact (1-5) | Risk Score (formula: =F*G) | Risk Level (formula) | Current Controls | Treatment | Residual Risk | Owner | ISO 27001 Control
R-001 | Ransomware attack on production database | AWS RDS (PHI database) | External threat actor | Unpatched OS, phishing entry point | 3 | 5 | 15 | High | WAF, EDR, monthly patching, MFA | Mitigate — implement immutable backups, improve patch SLA to 15 days | 8 | CISO | A.8.7, A.8.8, A.12.3
R-002 | Unauthorized PHI access by insider | MediSync Care Platform | Malicious or negligent employee | Overly broad access rights, no DLP tool | 3 | 5 | 15 | High | Role-based access, quarterly access reviews, Splunk logging | Mitigate — implement DLP, add user behavior analytics to Splunk | 9 | IT Manager | A.8.2, A.8.3, A.5.15
R-003 | Third-party EHR vendor breach exposing PHI | FHIR API integration layer | Compromised third-party vendor | Insufficient vendor security assessment frequency | 2 | 5 | 10 | High | BAAs in place, annual vendor security review | Mitigate — implement quarterly vendor reviews, add API rate limiting and anomaly detection | 6 | GRC Analyst | A.5.19, A.5.20, A.5.21
R-004 | Misconfigured AWS S3 bucket exposing PHI publicly | AWS S3 (PHI storage) | External attacker or accidental misconfiguration | Lack of automated cloud configuration monitoring | 2 | 5 | 10 | High | AWS CloudTrail enabled, manual S3 policy reviews | Mitigate — enable AWS Config rules for S3 public access blocking, implement automated misconfiguration alerts | 4 | Security Engineer | A.8.9, A.8.10, A.5.23
R-005 | Phishing attack leading to credential compromise | Employee credentials, email system | External threat actor via social engineering | Employees susceptible to phishing, no anti-phishing simulation program | 4 | 4 | 16 | Critical | MFA enabled, email filtering, annual security awareness training | Mitigate — implement quarterly phishing simulations, deploy anti-phishing email gateway | 8 | CISO | A.6.3, A.8.7, A.5.14
R-006 | SQL injection attack on Care Platform web app | MediSync Care Platform, AWS RDS | External attacker | Insufficient input validation, no WAF rule tuning | 2 | 5 | 10 | High | WAF deployed, code reviews conducted, OWASP guidelines followed | Mitigate — implement parameterized queries across all endpoints, conduct annual penetration test | 4 | Security Engineer | A.8.24, A.8.25, A.8.26
R-007 | Loss or theft of employee laptop containing PHI | Company-issued employee laptops | Physical theft or accidental loss | PHI cached locally on endpoints, no full disk encryption verification | 2 | 4 | 8 | Medium | MDM enrolled, remote wipe capability, VPN required | Mitigate — enforce full disk encryption via MDM policy, prohibit local PHI storage | 3 | IT Manager | A.7.8, A.7.9, A.8.1
R-008 | AWS region outage causing platform unavailability | MediSync Care Platform, AWS us-east-1 | Cloud provider infrastructure failure | Disaster recovery failover not tested, RTO unverified | 2 | 4 | 8 | Medium | DR environment in us-west-2, automated backups, Route 53 failover configured | Mitigate — conduct quarterly DR failover tests, document and validate RTO of 4 hours | 4 | CTO | A.8.13, A.8.14, A.5.29
R-009 | Weak password policy enabling brute force | Okta identity platform, all internal systems | External attacker or credential stuffing | Password policy not fully aligned to NIST SP 800-63B | 3 | 3 | 9 | Medium | MFA required, Okta lockout policy after 5 failed attempts | Mitigate — enforce 12-character minimum, disable password expiration per NIST guidance, implement breached password detection | 3 | IT Manager | A.8.5, A.5.16, A.5.17
R-010 | Failure to detect security incident due to SIEM gap | Splunk Cloud SIEM | Internal or external attacker operating undetected | Alert rules not fully tuned, high false positive rate masking real threats | 3 | 4 | 12 | High | Splunk Cloud deployed, basic alert rules configured | Mitigate — dedicate security engineer time to Splunk tuning, implement UEBA rules, conduct monthly alert review | 6 | Security Engineer | A.8.15, A.8.16, A.5.25
R-011 | Unpatched vulnerabilities in web application dependencies | MediSync Care Platform codebase | External attacker exploiting known CVEs | No automated dependency scanning in CI/CD pipeline | 3 | 4 | 12 | High | Qualys vulnerability scanning monthly, manual code reviews | Mitigate — implement automated dependency scanning (Dependabot or Snyk), reduce critical CVE patch SLA to 15 days | 5 | Security Engineer | A.8.8, A.8.25, A.8.26
R-012 | Unauthorized physical access to Cleveland HQ server room | On-premises servers, domain controller | Unauthorized internal or external individual | No CCTV coverage of server room, badge access logs not regularly reviewed | 1 | 4 | 4 | Low | Badge access required, locked server room, visitor log maintained | Mitigate — install CCTV in server room, implement monthly badge access log review | 2 | IT Manager | A.7.1, A.7.2, A.7.3
R-013 | Employee sharing PHI via unauthorized Slack channel | PHI, Slack communications platform | Negligent employee | No DLP controls on Slack, PHI-prohibition policy not consistently enforced | 3 | 3 | 9 | Medium | Acceptable use policy in place, Slack PHI prohibition communicated at onboarding | Mitigate — implement Slack DLP integration, add PHI detection keywords, conduct refresher training | 4 | GRC Analyst | A.5.10, A.6.3, A.8.11
R-014 | Business Associate Agreement not updated after HIPAA changes | Customer BAAs, HIPAA compliance program | Regulatory non-compliance | No formal BAA review cycle tied to regulatory update monitoring | 2 | 4 | 8 | Medium | BAAs in place with all 47 hospital customers, legal counsel reviews annually | Mitigate — implement BAA review trigger process tied to HHS regulatory updates, review all BAAs within 90 days of any HIPAA amendment | 3 | GRC Analyst | A.5.19, A.5.31, A.5.32
R-015 | Disaster recovery plan not tested — unknown RTO capability | Business continuity and DR plan | Operational failure during real disaster event | DR plan exists but annual tabletop exercises not conducted | 2 | 4 | 8 | Medium | DR plan documented, AWS us-west-2 DR environment provisioned | Mitigate — conduct semi-annual DR tabletop exercises and quarterly automated failover tests, document results | 3 | CTO | A.5.29, A.5.30, A.8.13
R-016 | Terminated employee retaining system access | All internal systems, Okta identity platform | Disgruntled former employee | No automated deprovisioning tied to HR offboarding workflow | 2 | 4 | 8 | Medium | IT Manager manually revokes access upon HR notification | Mitigate — automate deprovisioning via Okta-HR system integration, enforce same-day access revocation SLA | 2 | IT Manager | A.5.18, A.6.5, A.8.2
R-017 | Insufficient encryption of PHI data in transit | PHI transmitted via FHIR API and web application | Man-in-the-middle attack, network interception | TLS configuration not regularly audited, older TLS versions potentially enabled | 2 | 5 | 10 | High | TLS 1.2 enforced on web application, HTTPS required | Mitigate — enforce TLS 1.3 minimum across all endpoints, conduct quarterly TLS configuration audit using SSL Labs | 3 | Security Engineer | A.8.24, A.8.20, A.8.21
R-018 | Security awareness training completion below 95% | Employee security awareness program | Uninformed employees susceptible to social engineering | No automated training completion tracking or escalation process | 3 | 2 | 6 | Medium | Annual security awareness training assigned via LMS, completion tracked manually | Mitigate — implement automated completion tracking with manager escalation for non-completions, add quarterly micro-training modules | 2 | GRC Analyst | A.6.3, A.5.4, A.6.8
R-019 | Missing asset inventory for shadow IT devices | Corporate network, unmanaged endpoints | Unmanaged devices introducing vulnerabilities | No automated network discovery tool, asset inventory maintained manually in spreadsheet | 3 | 3 | 9 | Medium | MDM enrollment required for company devices, network access restricted via policy | Mitigate — deploy network discovery tool (Lansweeper or similar), integrate with asset inventory, conduct quarterly reconciliation | 4 | IT Manager | A.8.1, A.8.9, A.5.9
R-020 | Inadequate retention of audit logs for forensic use | Splunk Cloud logs, AWS CloudTrail logs | Inability to investigate security incidents or meet compliance requirements | Log retention period not formally defined or enforced across all systems | 2 | 3 | 6 | Medium | CloudTrail enabled, Splunk Cloud retaining 90 days of logs | Mitigate — define formal log retention policy (minimum 1 year for HIPAA compliance), implement archival to S3 Glacier for cost-effective long-term retention | 2 | GRC Analyst | A.8.15, A.8.16, A.5.28

## Methodology
Likelihood Scale
1 = Rare (less than once every 5 years) 2 = Unlikely (once every 2–5 years) 3 = Possible (once per year) 4 = Likely (multiple times per year) 5 = Almost certain (monthly or more)
Impact Scale
1 = Negligible (no PHI exposure, minimal disruption) 2 = Minor (limited PHI exposure under 500 records, <4hr outage) 3 = Moderate (500–5000 PHI records, 4–24hr outage, regulatory notice) 4 = Major (5000–50000 PHI records, >24hr outage, HHS notification) 5 = Catastrophic (>50000 PHI records, platform loss, criminal liability)
RISK SCORE = Likelihood × Impact
RISK LEVELS:
1–4 = Low (accept or monitor) 5–9 = Medium (mitigate within 90 days) 10–15 = High (mitigate within 30 days) 16–25 = Critical (immediate action required)
RISK APPETITE: MediSync will not accept residual risk scores above 9 for systems processing PHI.